Solicitation 36C24E26Q0054 — Good Clinical Practice (GCP) Clinical Research Quality Associate (CRQA) Monitoring Services

Section 3 Redacted Staffing Plan

1. Staffing Model

[OFFEROR] staffs this requirement with a two-tier structure sized to SMART's stated workload of 8 to 12 actively monitored trials per year within a 25-trial portfolio.

- Named CRQA monitor(s): [MONITOR NAME(S) — senior CRQA(s), each meeting every PWS 7.3 element: 7.3.2 credential (degree/licensure/CCRA), documented GCP training (7.3.3), monitoring/HSP training or CCRA (7.3.4), 10+ years GCP clinical-trial monitoring of research sites (7.3.5), and 5+ years monitoring/auditing federally funded research (7.3.6) with the trial-by-trial listing at 7.3.6.1; contingent offer executed; full documentation enclosed in Qualification Support Docs] [redact names]. Performs monitoring visits from the first task order.

- Program management and single point of accountability: the proposed Lead CRQA — ACRP-certified with documented GCP and human subjects protection training and extensive site-side GCP clinical research operations experience across multi-site federal (NIH) and industry protocols. Manages scheduling, credential currency, deliverable timeliness tracking, and escalation; administrative quality review (completeness, format, grammar, timeliness) of deliverables before release. Monitoring findings and reports are authored and owned by the named CRQA monitors.

- Credential-verified bench: an active national recruiting pipeline (public careers page and national job boards) with 70+ applicants to date, screened against the full PWS 7.3 qualification set as the application gate; additional qualified monitors are engaged as task-order volume requires.

2. Task-Order Response (PWS 4.2 — 30 days)

Days 0–3: confirm scope and monitoring plan. Days 3–10: match monitor(s) from the bench and verify credential currency. Days 10–20: trial-specific onboarding (protocol, operations manual, SMART SOPs/AMPs). Days 20–30: readiness check by the Lead reviewer and submission of monitor identification with full PWS 7.3 documentation to SMART.

3. Continuity and Quality of Staffing

- Credential expiration tracking with 90-day alerts; no monitor performs with lapsed credentials, consistent with the Certifying Statement.

- A cross-briefed backup monitor is designated for each active study, with a documented handover protocol for any transition.

- VA credentialing and PIV processing initiated at assignment and tracked to completion before the first site visit.

- Limitations on subcontracting (VAAR 852.219-75): W2 monitors constitute the required performance share, tracked each invoice period.