Solicitation 36C24E26Q0054 — Good Clinical Practice (GCP) Clinical Research Quality Associate (CRQA) Monitoring Services

Section 2 Staffing Plan

Pacific Research Group LLC · UEI J585TLDV1CH1 · CAGE 1Z9B6

1. Staffing Model

Pacific Research Group LLC staffs this requirement with a two-tier structure sized to SMART's stated workload of 8 to 12 actively monitored trials per year within a 25-trial portfolio.

- Primary CRQA: [CANDIDATE NAME — CCRA-certified; contingent offer executed; certificates enclosed in Qualification Support Docs]. Performs monitoring visits from the first task order.

- Second monitor and single point of accountability: Andrew O'Donnell, Managing Director — ACRP-certified with documented GCP, human subjects protection, and clinical monitoring training [course certificate enclosed], and extensive site-side GCP operations experience across multi-site federal (NIH) and industry protocols. Quality-reviews every deliverable before release and serves as escalation and scheduling POC.

- Credential-verified bench: an active national recruiting pipeline (public careers page and national job boards) with 70+ applicants to date, screened against PWS 7.3 as the application gate; additional monitors are engaged as task-order volume requires.

2. Task-Order Response (PWS 4.2 — 30 days)

Days 0–3: confirm scope and monitoring plan. Days 3–10: match monitor(s) from the bench and verify credential currency. Days 10–20: trial-specific onboarding (protocol, operations manual, SMART SOPs/AMPs). Days 20–30: readiness check by the Lead reviewer and submission of monitor identification with full PWS 7.3 documentation to SMART.

3. Continuity and Quality of Staffing

- Credential expiration tracking with 90-day alerts; no monitor performs with lapsed credentials, consistent with the Certifying Statement.

- A cross-briefed backup monitor is designated for each active study, with a documented handover protocol for any transition.

- VA credentialing and PIV processing initiated at assignment and tracked to completion before the first site visit.

- Limitations on subcontracting (VAAR 852.219-75): W2 monitors and any similarly-situated SDVOSB subcontractors constitute the required performance share, tracked each invoice period.